## Sheet1
SYSADD
ACTIVITY | START DATE | NUMBER OF DAYS
Preparing and reviewing the assigned project for further changes and developments. | 2016-06-09 | 1
Starting to organize project. Creating Project Schedule for month of June. Preparing Project Adviser & Consultant Forms Learning how to use github for repository | 2016-06-13 | 5
Project meeting. Conceptualization of work flow. Preparing Project Request Forms | 2016-06-16 | 3
Consulting a Project Adviser on IT Professors Meeting with the Client. Project Meeting | 2016-06-20 | 4
Creating APC Projects Wiki,Project Meeting | 2016-06-23 | 3
Meeting with the client. | 2016-06-25 | 2
Learning how to use repository Discussing Project within the class | 2016-06-27 | 2
Creating draft of Diagrams,Project Meeting | 2016-06-28 | 1
Signing of Project Adviser proposal. | 2016-06-29 | 1
Data Gathering on Client. Establishing diagrams. Project Meeting , Scheduling of task in month of July | 2016-07-04 | 5
Meeting with the Client. | 2016-07-06 | 2
Project Meeting Preparing project documentation | 2016-07-07 | 1
Discussing with other resources Updating Projects Wiki | 2016-07-08 | 1
Checking drafts of Diagrams Creating the remaining diagrams. Project Meeting | 2016-07-04 | 4
Discussing drafts of Diagrams within the class Project Meeting | 2016-07-07 | 1
Project Planning for Project Content | 2016-07-11 | 4
Discussing drafts of Diagrams within the class Project Meeting Organizing Projects Wiki & other requirements | 2016-07-14 | 3
Project Meeting , Establishing Project Content | 2016-07-18 | 4
Discussion with Project Adviser | 2016-07-19 | 1
Finalizing Project Contents Uploading requirements on OneNote and Project Wiki | 2016-07-20 | 1
Discussion with Project Adviser Project Presentation for Midterm | 2016-07-21 | 1
Discussing with Project Adviser | 2016-07-25 | 4
First Project Presentation | 2016-07-25 | 1
Revision of Project. Project Content and Event Table | 2016-07-26 | 1
Meeting the client for reviews of the project | 2016-07-27 | 1
Project Meeting Discussing with project adviser | 2016-07-28 | 1
Revision of Project | 2016-08-01 | 4
Discussion with project professor | 2016-08-02 | 1
Project Meeting | 2016-08-02 | 1
Project Meeting Schedule of Presentation will be on August 22 Planning for Application Prototype | 2016-08-04 | 2
Developing Prototype Application Modifying event table and other diagrams | 2016-08-08 | 4
Meeting and discussion with client | 2016-08-09 | 1
Endorsing schedule of final project presentation to our client. (approved August 22, 2016) | 2016-08-10 | 1
Finalizing documentation Developing Prototype Application Design | 2016-08-11 | 1
Finalizing documentation Developing Prototype Application with Database | 2016-08-15 | 4
Meeting and discussion with client | 2016-08-17 | 2
Finalizing documentation Developing Prototype Application | 2016-08-18 | 1
Updating OneNote, Git hub and Projects Wiki | 2016-08-21 | 3
Finalizing Prototype Application and Projects Documentation | 2016-08-21 | 1
Uploading Application and Database screenshots | 2016-08-21 | 1
Finalizing Project Status Reports | 2016-08-21 | 1
CSPROJ
Preparing requirements for CSPROJ2, Creating IBM Account | 2016-09-20
Meeting with the client, Creating project schedule, Updating repository and documentation | 2016-09-21
Project meeting, Discussion about IBM Bluemix, Using IBM Cloudfoundry | 2016-09-23
Endorsing Project Adviser and Consultant, Creating Project Status Report | 2016-09-26
Using IBM Bluemix (phpmyadmin, mysql-service, samplephp) cloudfoundry | 2016-09-27
Meeting with the client. | 2016-09-28
Project meeting, Class discussion about cloudfoundry | 2016-09-30
Project Meeting, Discussion of Project Vision & Scope | 2016-10-04
Meeting with the client. | 2016-10-05
Updating GitHub Repository, Planning for Project Vision & Scope | 2016-10-07
Creating Project Vision and Scope, Project Meeting and Class Discussion | 2016-10-11
Creating Project Statement of Work | 2016-10-12
Finalizing Version 1.0 Draft of Project Vision and Scope and Statement of Work | 2016-10-14
Fixing bugs and errors on BlueMix, Project Meeting | 2016-10-18
Creating Gantt Chart | 2016-10-19
Presentation of Project Vision and Scope Version 1 and Project Statement of Work. | 2016-10-21