## Sheet1
Activity | Activity Name | Activity Name Description | # of Days | Start Date
1 | Project Team meeting | Planning | 1 | 2016-09-06
1.1 | Reviewing Business Process | Planning | 14 | 2016-10-06
1.2 | Data and Resources gathering | Planning | 11 | 06/24/2016
1.3 | Preparing Project Consultant and Adviser | Planning | 3 | 2016-05-07
2 | Business Logic of System | Analysis | 5 | 2016-07-07
2.1 | System Models | Analysis | 3 | 07/14/2016
2.2 | Visualizing Design | Analysis | 10 | 07/15/2016
3 | System Architecture and Logic (Prototype) | Design | 9 | 07/25/2016
3.1 | System Design (Prototype) | Design | 11 | 2016-03-08
3.2 | User Interface | Design | 3 | 08/14/2016
4 | Git Repository | Development | 2 | 08/16/2016
4.1 | OneNote | Development | 1 | 08/18/2016
4.2 | APC Wiki | Development | 2 | 08/19/2016
5 | Consultation with Project Client and Adviser | Testing | 1 | 08/21/2016
5.1 | Defense with Client and Panelist | Testing | 1 | 08/22/2016
6 | Fixing errors and bugs | Deployment | 12 | 09/19/2016
6.1 | Improvement on the System | Deployment | 33 | 2016-01-10
6.2 | Support | Deployment | 14 | 2016-05-11
6.3 | Maintenance | Deployment | 15 | 11/19/2016
6.4 | Installation of the System | Deployment | 13 | 2016-04-12